## All AI Features
EEC ML — All AI Features
# | Feature | Status | Progress % | In Old CSV? | Files / Location | What's Missing
── 1. CORE AI PIPELINE ──────────────────────────────────────────────────────────────────────────────────────
1 | Document Ingestion (OCR → Parse → Chunk → Embed → Qdrant) | ✅ Done | 95% | Yes | ai-service/app/modules/documents/ | Bloom + learning-outcome + topic tagging now run on ingest; legacy chunks need re-index
2 | AI Orchestrator (central workflow coordinator) | ✅ Done | 85% | No | NEEDED: ai-service/app/orchestrator/ | POST /orchestrate dispatch live; ingest/OCR/speech/vision still called directly by design
3 | RAG Engine (semantic retrieval with metadata filtering) | ✅ Done | 95% | Yes | ai-service/app/modules/retrieval/ | Hybrid BM25+semantic (RRF) now merged in; fusion weights untuned
4 | Hybrid Search (BM25 keyword + semantic vector) | ✅ Done | 85% | No | NEEDED in retrieval/service.py | Reciprocal-rank-fusion of vector + keyword hits in retrieval/service.py; weight tuning pending
5 | Embedding Engine (nomic-embed-text via Ollama) | ✅ Done | 95% | No | ai-service/app/modules/embeddings/ | Fully wired
6 | Prompt Library (externalised /prompts/ directory) | ✅ Done | 85% | No | NEEDED: ai-service/prompts/ | ai-service/prompts/ + loader.py (~50 files); a few module prompts still inline
── 2. CONTENT INTELLIGENCE ─────────────────────────────────────────────────────────────────────────────────
7 | Curriculum Graph (topic → prerequisite map) | 🔶 Partial | 60% | Yes | backend/models/CurriculumMap.js + curriculumMapRoutes.js | Prerequisite traversal via gapDetectionEngine; no auto-update on ingest, manual curriculum entry
8 | Learning Outcomes Auto-generation from documents | ✅ Done | 80% | No | NEEDED in documents/service.py | classifier/outcomes.extract_learning_outcomes runs on ingest; legacy docs need re-index
9 | Bloom Engine (tag documents + questions + answers) | ✅ Done | 85% | No | NEEDED: ai-service/app/modules/bloom/ | classifier/bloom on ingest + retrieval filter + question-gen + mastery progression; legacy chunks need re-index
10 | Document Versioning (retain old versions, never auto-delete) | 🔶 Partial | 60% | No | NEEDED in TeachingMaterial.js | TeachingMaterial.versions[] + isEnabled (disable-not-delete) exist; no auto-version-on-reupload, no version-browse UI
11 | Question Bank (permanent store, teacher-editable) | ✅ Done | 80% | Yes | backend/models/ExamQuestion.js + PracticeQuestion.js | GeneratedQuestion store + teacher save/list/edit/approve APIs; no difficulty calibration
── 3. ASSESSMENT & EVALUATION ─────────────────────────────────────────────────────────────────────────────
12 | Academic Assessment Engine (MCQ + written answer eval) | ✅ Done | 80% | Yes | ai-service/app/modules/assessment/ | MCQ + written + long-answer all evaluated; dedicated long-answer student workflow (LongAnswerQuestion/Submission + /api/long-answer-assessments) now built; live replica-set DB verification pending
13 | Language Reading Assessment (Qwen3 8B scoring) | ✅ Done | 95% | Yes | ai-service + ReadingAssessment.js + ReadingPracticePage.jsx | End-to-end pipeline working
14 | Language Writing Assessment (Qwen3 8B scoring) | ✅ Done | 95% | Yes | ai-service + WritingAssessment.js + WritingPracticePage.jsx | End-to-end pipeline working
15 | Answer Evaluator — full rubric (marks/rubric/Bloom/confidence/missing concepts/mastery update) | 🔶 Partial | 75% | No | ai-service/app/modules/assessment/service.py | Marks/rubric/Bloom/confidence/missing-concepts persisted on exam + assignment + long-answer submissions; needs-review gating + teacher-override supersede wired
16 | Error Classification Engine (Concept/Calculation/Reading/Logic) | ✅ Done | 85% | Yes | NEEDED: ai-service/app/modules/error_classifier/ | backend/services/errorClassifier.js + ai-service classifier — Concept/Calculation/Reading/Logic all classified
17 | Baseline Quiz (initial mastery estimate) | ✅ Done | 90% | Yes | backend/models/BaselineQuiz.js + BaselineQuiz.jsx | Results feed mastery via masteryEventService
── 4. MASTERY & MEMORY ─────────────────────────────────────────────────────────────────────────────────────
18 | Mastery Engine (score calculate + auto-update after every attempt) | ✅ Done | 85% | Yes | backend/services/masteryEngine.js + MasteryScore.js | Auto-update across baseline/tutor/practice/practice-paper/exam + immutable MasteryEvent history; replica-set txns + live verification pending
19 | ML Engine (weighted EMA mastery, at-risk detection, class trends) | 🔶 Partial | 65% | No | backend/services/mlEngine.js + mlRoutes.js | EMA + at-risk + class trends read assessment events; regression forecast not validated on longitudinal data
20 | Engagement Scorer (time × views × attempts per topic) | 🔶 Partial | 55% | No | backend/services/engagementScorer.js + engagementRoutes.js | Behavioural dimension only; teacher dashboard card pending
21 | Spaced Repetition Engine (SM-2 algorithm, review scheduling) | 🔶 Partial | 65% | No | backend/models/SpacedRepetitionSchedule.js + spacedRepetitionRoutes.js | SM-2 + cron nudges + recommendation tie-in; not auto-triggered from every quiz result
22 | Student Academic Memory (weak topics, past mistakes, study history) | 🔶 Partial | 58% | No | NEEDED: extend StudentMemorySummary.js | StudentMemorySummary + /academic-memory + retention/prune sweep; summarisation pipeline still partial
23 | Conversation Memory (persisted cross-session) | 🔶 Partial | 65% | No | TutorConversation.js exists; no cross-session recall | TutorConversation persisted + rolling summarise + retention policy (prune 365d, purge on exit) + admin purge endpoint; cross-session recall still summary-only
── 5. GAP DETECTION & LEARNING PATH ───────────────────────────────────────────────────────────────────────
24 | Gap Detection Engine (traverse graph → root-cause weak topics) | ✅ Done | 80% | Yes | NEEDED: ai-service/app/modules/gap_detector/ | gapDetectionEngine.js — prerequisite traversal + root-cause weak-topic detection; depends on error-classifier signal quality
25 | Recommendation Engine (next topic + material based on mastery) | ✅ Done | 80% | No | backend/routes/recommendationRoutes.js | recommendationEngine.js + acceptance/completion/impact tracking (RecommendationEvent); frontend widget wiring pending
26 | AI-generated Learning Path (bridge from gap → target topic) | 🔶 Partial | 55% | Yes | NEEDED in ai-service; TeacherLearningPath.js exists for manual | Weekly plan generated from mastery + recs; AI bridge-path for an arbitrary gap→target still limited
27 | Personalised Study Plan (week-by-week schedule output) | ✅ Done | 80% | Yes | NEEDED: integrate gap → path → study plan generator | weeklyStudyPlanService + WeeklyStudyPlan + GET/PATCH /api/study-plans/*; no calendar export
── 6. AI CONTENT GENERATION (Student) ─────────────────────────────────────────────────────────────────────
28 | AI Tutor Chat — Explain Mode | ✅ Done | 92% | No | ai-service/app/modules/chat/ (mode=explain) | Mode works
29 | AI Tutor Chat — Homework Help (Socratic) | ✅ Done | 95% | Yes | ai-service/app/modules/chat/ (mode=homework_help) | 7-rule Socratic enforcement active
30 | AI Tutor Chat — Summarize Mode | ✅ Done | 92% | Yes | ai-service/app/modules/summaries/ | Works well
31 | AI Tutor Chat — Notes Mode | ✅ Done | 92% | Yes | ai-service/app/modules/chat/ (mode=notes) | POST /save-note + GET /saved-notes added
32 | AI Tutor Chat — Quiz Mode | ✅ Done | 90% | Yes | ai-service/app/modules/quiz/ + QuizUI | Quiz results not yet auto-saved to Question Bank
33 | AI Tutor Chat — Flashcard Mode | ✅ Done | 92% | Yes | ai-service/app/modules/flashcards/ + FlashcardUI | flashcard-rating persists to mastery via applyAssessment
34 | AI Tutor Chat — Mind Map Mode | ✅ Done | 90% | Yes | ai-service/app/modules/chat/ (mode=mind_map) + MindMapUI | No PDF/image export
35 | Worksheet / Homework Generation (personalised to mastery gaps) | 🔶 Partial | 50% | No | NEEDED in ai-service chat module | POST /api/ai-teacher/worksheet generates worksheets; not personalised to individual mastery gaps
36 | Adaptive Difficulty (adjust question hardness based on mastery) | 🔶 Partial | 60% | No | NEEDED: wire MasteryScore into quiz/question generation | Mastery-derived Bloom band drives question difficulty; no full IRT/adaptive item selection
── 7. AI CONTENT GENERATION (Teacher) ─────────────────────────────────────────────────────────────────────
37 | AI Lesson Content Generator (teacher-facing) | 🔶 Partial | 55% | No | backend/routes/aiTeacherRoutes.js (mode=lesson-content) | aiTeacherRoutes lesson-content + prompts/evaluation/lesson_content.txt
38 | AI Hinge Question Generator (teacher-facing) | 🔶 Partial | 55% | No | backend/routes/aiTeacherRoutes.js (mode=hinge-questions) | aiTeacherRoutes hinge-questions + prompts/question_generation/hinge_question.txt
39 | AI Question Paper Generator (teacher selects topic + Bloom) | 🔶 Partial | 55% | No | mockExamRoutes.js generates questions; no Bloom param | Bloom-level question generation exists (bloom_question.txt); teacher UI for Bloom/difficulty selection pending
40 | Teacher AI Override (correct/edit an AI answer) | ✅ Done | 80% | No | NEEDED: teacher annotation layer | POST/DELETE /api/ai-tutor/teacher/correct-answer + GET /teacher/corrections; audited, allocation-scoped, joined onto reads. Frontend affordance pending
── 8. LANGUAGE ASSESSMENT ─────────────────────────────────────────────────────────────────────────────────
41 | Speech Transcription (faster-whisper) | ✅ Done | 85% | Yes | ai-service/app/modules/speech/service.py | faster-whisper large-v3-turbo; slow-hardware latency untested
42 | Pronunciation Scoring (SpeechBrain) | ✅ Done | 85% | Yes | ai-service/app/modules/speech/pronunciation.py | wav2vec2 pronunciation scoring; real-device mic testing pending
43 | Student Language Profile (adaptive Qdrant memory) | ✅ Done | 82% | Yes | StudentLanguageProfile.js + language_memory module | Qdrant memory active; not surfaced as a student dashboard card
── 9. ANALYTICS & INTELLIGENCE ────────────────────────────────────────────────────────────────────────────
44 | Teacher Analytics Dashboard (class performance) | 🔶 Partial | 70% | Yes | teacherAnalyticsRoutes.js | At-risk list + risk scores + mastery heatmap + gap results + Bloom distribution; analytics authz hardened; live DB verification + polish pending
45 | Admin Analytics Dashboard (school-level AI metrics) | 🔶 Partial | 55% | Yes | adminAnalyticsRoutes.js | Admin AI performance insights live; subject weak-area report pending
46 | Student Progress Dashboard (unified mastery + gaps + path) | ✅ Done | 75% | Yes | MasteryView.jsx + LearningPathMapView.jsx | Unified GET /health-card (mastery + gaps + SR + language + recs); frontend still shows independent views
47 | At-risk Student Detection (ML engine flag) | ✅ Done | 80% | No | backend/services/mlEngine.js (GET /class/at-risk) | Weak/at-risk list + attendance+assessment+trend scoring + scheduled scans + real-time alerts; forecast validation pending
48 | Class Engagement Analytics (per-topic engagement scores) | 🔶 Partial | 45% | No | backend/services/engagementScorer.js + engagementRoutes.js | engagementScorer + endpoint; no teacher dashboard card
49 | AI-generated Insights for Teacher ('Class struggles with X') | ✅ Done | 75% | No | NEEDED: LLM summarise analytics data | classLearningAnalytics + /class-insights LLM narrative over real mastery data; narrative-quality eval pending
50 | Wellbeing Tracking (student check-in + admin visibility) | 🔶 Partial | 60% | No | backend/models/Wellbeing.js + wellbeingRoute.js | Wellbeing check-in now auto-escalates critical/concerning moods to principal + counselling via EscalationCase; safeguarding disclosure form + confidential handling still pending
── 10. RESEARCH-GRADE FEATURES (from Area to Cover doc) ───────────────────────────────────────────────────
51 | Learner Confidence Tracking (dynamic self-perception) | ❌ Not Started | 0% | No | NEEDED: new model + AI check-in | No model, no UI, no data collection
52 | Help-Seeking Behaviour (log when/how student asks for help) | ❌ Not Started | 0% | No | NEEDED: event logging in tutor session | No tracking mechanism
53 | Retention / Forgetting Model (knowledge decay over time) | 🔶 Partial | 45% | No | SpacedRepetitionSchedule.js + spacedRepetitionRoutes.js | SM-2 retention model built; not surfaced as a forgetting-curve view
54 | Misconceptions Engine (explicit error model per topic/student) | 🔶 Partial | 45% | No | NEEDED: extend error classifier output | Class-wide misconception aggregation (classMisconceptions) + misconception tutor mode; per-student explicit misconception model pending
55 | Multidimensional Engagement (situational + behavioural + emotional) | 🔶 Partial | 25% | No | engagementScorer.js (behavioural only) | Only behavioural dimension built; situational + emotional missing
56 | Intervention Effectiveness (measure what actually improves learning) | ✅ Done | 75% | No | NEEDED: analytics overlay on interventions | Auto follow-up plans + 7/14/30-day checkpoints + automatic improvement calc + auto-finalize; escalation to leadership + longitudinal validation pending
57 | Teacher Escalation (auto-flag students for human support) | ✅ Done | 75% | No | NEEDED: alert system from gap detection / at-risk engine | EscalationCase + escalationService: wellbeing distress + critical academic risk (riskScore>=85) auto-route to leadership + counselling, deduped weekly; /api/escalations acknowledge/action/resolve; manual teacher raise (scoped)
58 | Student Agency (learner control over learning path) | 🔶 Partial | 20% | No | NEEDED: student path selection UI + preference store | Student can accept/dismiss/complete recommendations; no learning-path selection UI
59 | Explainable AI (why did AI recommend / answer this?) | 🔶 Partial | 60% | No | NEEDED: reasoning trace in tutor response | AiInteractionLog records model/prompt/retrieval/latency/outcome per AI call + admin audit endpoint + ai-service lineage block; end-user reasoning-trace UI still pending
60 | Social / Belonging Dimension (peer signals + community) | ❌ Not Started | 0% | No | Alcove exists for posts; no belonging analytics | No social learning signals
61 | Evidence Testing (prove platform improves learning outcomes) | 🔶 Partial | 25% | No | NEEDED: pre/post measurement framework | Assessment-evidence summaries + daily regression forecast infra; no pre/post outcome-measurement framework, forecast unvalidated
62 | Equity / Bias Monitoring (detect uneven model performance) | ❌ Not Started | 0% | No | NEEDED: cohort-level analytics overlay | No bias detection
63 | Wellbeing Safeguards (child protection + human support boundary) | ❌ Not Started | 0% | No | NEEDED: escalation policy + safeguard layer | Wellbeing CRUD exists; no safeguard framework
64 | AI / Data Ethics Framework (child-centered, beyond RBAC) | 🔶 Partial | 20% | No | JWT + RBAC + tenant isolation done | JWT + RBAC + tenant isolation; no child-ethics/consent framework
── 11. FUTURE FEATURES (Architecture doc roadmap) ─────────────────────────────────────────────────────────
65 | Voice Tutor (speech-to-text + AI response + TTS) | ❌ Not Started | 0% | No | NEEDED: extend speech module | Speech transcription exists; full voice loop not wired
66 | Image Understanding (student uploads photo of problem) | 🔶 Partial | 50% | No | NEEDED: vision model integration (LLaVA/Qwen-VL) | vision module: POST /vision/explain-image + PDF-page vision on ingest + visual_explain mode; student photo-of-problem upload flow pending
67 | Video Understanding (lecture video → summary + quiz) | ❌ Not Started | 0% | No | NEEDED: video ingestion pipeline | No video processing
68 | Code Tutor (programming support + code review) | ❌ Not Started | 0% | No | NEEDED: code-specific prompt + execution sandbox | No code tutor mode
69 | Math Solver (step-by-step equation solving) | 🔶 Partial | 40% | No | NEEDED: math-aware model or tool (Qwen-Math) | stem module + stem/verifier.py math-answer verification; step-by-step solving UI + dedicated math model pending
70 | Topic Failure Prediction (predict fail before test happens) | 🔶 Partial | 25% | No | NEEDED: time-series model over mastery decay | learningEvidenceService.forecastScores infra; not validated, not surfaced
71 | Learning Style Detection (visual/reading/quiz preference) | ❌ Not Started | 0% | No | NEEDED: interaction log clustering | No interaction preference tracking
72 | Performance Forecasting (predicted score on next test) | 🔶 Partial | 30% | Yes | NEEDED: regression over mastery + engagement data | Daily least-squares score forecast (forecast-v1) + class forecast; accuracy not validated on longitudinal data
73 | At-risk / Dropout Risk Prediction (ML model) | 🔶 Partial | 35% | Yes | NEEDED: attendance + mastery + engagement pipeline | At-risk detection from attendance + mastery + trends; dedicated dropout-risk model not built

## Missing from Old CSV
EEC ML — Features Missing from Old CSV Checklist
Feature | Status | Progress % | Files / Location | Why It Was Missing
── ALREADY BUILT — but not in the old checklist ────────────────────────
Embedding Engine | ✅ Done | 95% | ai-service/app/modules/embeddings/ | Fully wired
Explain Mode (AI Tutor) | ✅ Done | 92% | ai-service chat module (mode=explain) | Mode works
ML Engine (EMA mastery) | 🔶 Partial | 65% | backend/services/mlEngine.js | EMA + at-risk + class trends on assessment events; forecast unvalidated
Engagement Scorer | 🔶 Partial | 55% | backend/services/engagementScorer.js | Behavioural dimension; no teacher card
Spaced Repetition (SM-2) | 🔶 Partial | 65% | backend/models/SpacedRepetitionSchedule.js | SM-2 + cron + recommendation tie-in
Recommendation Engine | ✅ Done | 80% | backend/routes/recommendationRoutes.js | Engine + acceptance/completion/impact tracking; frontend wiring pending
At-risk Student Detection | ✅ Done | 80% | backend/routes/mlRoutes.js (GET /class/at-risk) | Scheduled scans + real-time alerts + StudentInsight record
Engagement Analytics | 🔶 Partial | 45% | backend/routes/engagementRoutes.js | Endpoint live; no teacher card
AI Lesson Content (Teacher) | 🔶 Partial | 55% | backend/routes/aiTeacherRoutes.js (lesson-content) | Route + externalised prompt
AI Hinge Question (Teacher) | 🔶 Partial | 55% | backend/routes/aiTeacherRoutes.js (hinge-questions) | Route + externalised prompt
Wellbeing Tracking | 🔶 Partial | 40% | backend/models/Wellbeing.js + wellbeingRoute.js | Model + CRUD; no safeguard/escalation layer
Answer Evaluator (full) | 🔶 Partial | 75% | ai-service/app/modules/assessment/ | Missing-concept + confidence persisted on exam + assignment + long-answer; needs-review gating
── ARCHITECTURAL — not in old checklist ────────────────────────────────
AI Orchestrator | ✅ Done | 85% | NEEDED: ai-service/app/orchestrator/ | ai-service/app/modules/orchestrator/ — POST /orchestrate dispatch
Prompt Library | ✅ Done | 85% | NEEDED: ai-service/prompts/ | ai-service/prompts/ + loader.py (~50 files)
Hybrid Search (BM25+vector) | ✅ Done | 85% | NEEDED in retrieval/service.py | RRF fusion of vector + keyword hits in retrieval/service.py
Document Versioning | 🔶 Partial | 60% | NEEDED in TeachingMaterial.js | TeachingMaterial.versions[] + isEnabled; no auto-version-on-reupload / browse UI
Learning Outcomes Auto-gen | ✅ Done | 80% | NEEDED in documents/service.py | classifier/outcomes on ingest; legacy docs need re-index
Bloom Engine | ✅ Done | 85% | NEEDED: ai-service/app/modules/bloom/ | classifier/bloom on ingest + retrieval filter + question-gen + mastery progression
── CONTENT GENERATION — not in old checklist ──────────────────────────
Worksheet / Homework Gen | 🔶 Partial | 50% | NEEDED in chat module | POST /api/ai-teacher/worksheet; not personalised to mastery gaps
Adaptive Difficulty | 🔶 Partial | 60% | NEEDED: wire MasteryScore → content generation | Mastery→Bloom band drives difficulty; no full adaptive item selection
AI Question Paper (Teacher) | 🔶 Partial | 55% | NEEDED: Bloom + difficulty param in exam gen | Bloom-level question gen exists; teacher selection UI pending
Teacher AI Override | ✅ Done | 80% | NEEDED: annotation layer on AI responses | correct-answer + withdraw + list endpoints; audited + allocation-scoped; frontend pending
── RESEARCH-GRADE — not in old checklist ──────────────────────────────
Learner Confidence | ❌ Not Started | 0% | NEEDED: new model + AI check-in flow | No data collection
Help-Seeking Behaviour | ❌ Not Started | 0% | NEEDED: event logging in tutor session | No tracking
Misconceptions Engine | 🔶 Partial | 45% | NEEDED: extend error classifier | Class-wide aggregation + tutor mode; per-student model pending
Multidimensional Engagement | 🔶 Partial | 25% | engagementScorer.js (behavioural only) | Situational + emotional dimensions missing
Intervention Effectiveness | ✅ Done | 75% | NEEDED: analytics on interventions | Auto follow-up + 7/14/30-day checkpoints + automatic improvement calc + auto-finalize
Teacher Escalation | 🔶 Partial | 35% | NEEDED: alert from gap/at-risk engine | Auto intervention-plan creation on alert; counsellor/leadership escalation not built
Student Agency | 🔶 Partial | 20% | NEEDED: path selection UI | Accept/dismiss/complete recommendations; no path-selection UI
Explainable AI | 🔶 Partial | 25% | NEEDED: reasoning trace in tutor response | Explainability string on recs; no reasoning-trace/lineage logging
Social / Belonging | ❌ Not Started | 0% | Alcove posts exist; no belonging analytics | No social learning signals
Evidence Testing | 🔶 Partial | 25% | NEEDED: pre/post outcome measurement | Evidence summaries + forecast infra; no pre/post framework
Equity / Bias Monitoring | ❌ Not Started | 0% | NEEDED: cohort analytics overlay | No bias detection
Wellbeing Safeguards | ❌ Not Started | 0% | NEEDED: escalation policy + child protection | Wellbeing CRUD exists; no safeguard layer
AI / Data Ethics Framework | 🔶 Partial | 20% | JWT + RBAC + tenant isolation done | RBAC + tenant isolation; no child-ethics/consent framework
── FUTURE — not in old checklist ──────────────────────────────────────
Voice Tutor | ❌ Not Started | 0% | Extend speech module | Transcription exists; full voice loop not wired
Image Understanding | 🔶 Partial | 50% | NEEDED: vision model (LLaVA/Qwen-VL) | vision module + explain-image + PDF-page vision + visual_explain mode; student upload flow pending
Video Understanding | ❌ Not Started | 0% | NEEDED: video ingestion pipeline | No video processing
Code Tutor | ❌ Not Started | 0% | NEEDED: code-mode prompt + sandbox | No code tutor mode
Math Solver | 🔶 Partial | 40% | NEEDED: math model (Qwen-Math) | stem/verifier.py math-answer verification; step-by-step UI + math model pending
Topic Failure Prediction | 🔶 Partial | 25% | NEEDED: time-series over mastery decay | forecastScores infra; unvalidated, not surfaced
Learning Style Detection | ❌ Not Started | 0% | NEEDED: interaction log clustering | Not started

## Backend Models
EEC ML — Backend Models
Model File | Purpose | Status | Progress % | Route File | Notes / Gaps
── AUTH & USERS ─────────────────────────────────────────────────────────
Admin.js | Admin user schema | ✅ Done | 100% | adminRoutes.js | Full CRUD + RBAC
ParentUser.js | Parent account | ✅ Done | 100% | parentRoute.js | Full portal
Principal.js | Principal account | ✅ Done | 100% | principalRoutes.js | Full portal
StaffUser.js | Non-teaching staff | ✅ Done | 100% | staffRoutes.js | Full portal
StudentUser.js | Student account | ✅ Done | 100% | studentRoute.js | Full portal
TeacherUser.js | Teacher account | ✅ Done | 100% | teacherRoute.js | Full portal
SuperAdminActivity.js | Super-admin audit log | ✅ Done | 100% | superAdminRoutes.js | Audit trail
── SCHOOL STRUCTURE ────────────────────────────────────────────────────
Organization.js | Top-level tenant | ✅ Done | 100% | organizationRoutes.js | Multi-tenant root
School.js | School entity | ✅ Done | 100% | schoolRoutes.js | Full CRUD
AcademicYear.js | Academic year | ✅ Done | 100% | academicRoutes.js | Full CRUD
Class.js | Class / grade | ✅ Done | 100% | academicRoutes.js | Full CRUD
Section.js | Section in class | ✅ Done | 100% | academicRoutes.js | Full CRUD
Subject.js | Subject entity | ✅ Done | 100% | subjectRoute.js | Full CRUD
Department.js | Teacher department | ✅ Done | 100% | departmentRoutes.js | Full CRUD
Timetable.js | Class timetable | ✅ Done | 100% | timetableRoutes.js | Full CRUD
Building.js | Campus building | ✅ Done | 100% | — | Reference data
Floor.js | Floor in building | ✅ Done | 100% | — | Reference data
Room.js | Classroom entity | ✅ Done | 100% | — | Reference data
Holiday.js | Holiday calendar | ✅ Done | 100% | holidayRoutes.js | Full CRUD
TeacherAllocation.js | Teacher → class-subject | ✅ Done | 100% | teacherAllocationRoutes.js | Full CRUD
── ACADEMIC & EXAMS ────────────────────────────────────────────────────
Assignment.js | Assignment + submissions | ✅ Done | 100% | assignmentRoute.js | Full CRUD
Exam.js | Exam entity | ✅ Done | 100% | examRoute.js | Full CRUD
ExamAttempt.js | Student exam attempt | ✅ Done | 100% | examRoute.js | Recorded
ExamGroup.js | Exam grouping | ✅ Done | 100% | examRoute.js | Full CRUD
ExamQuestion.js | MCQ/short/long question | 🔶 Partial | 60% | examRoute.js | Evaluator wired for written answers; no Bloom/difficulty calibration
ExamResult.js | Exam result record | ✅ Done | 100% | examRoute.js | Full CRUD
LessonPlan.js | Teacher lesson plan | ✅ Done | 100% | lessonPlanRoutes.js | Full CRUD
LessonPlanCompletion.js | Lesson completion track | ✅ Done | 100% | lessonPlanRoutes.js | Tracked
ReportCardTemplate.js | Report card template | ✅ Done | 100% | reportRoutes.js | Full CRUD
TeachingMaterial.js | Teacher-uploaded material | ✅ Done | 100% | teachingMaterialRoutes.js | Cloudinary + Qdrant ingest
Rubric.js | Grading rubric | 🔶 Partial | 70% | rubricRoutes.js | Rubric assignments now use the AI evaluator
PromotionHistory.js | Student promotion record | ✅ Done | 100% | promotionRoutes.js | Full CRUD
── AI & LEARNING ───────────────────────────────────────────────────────
CurriculumMap.js | Topic prerequisite graph | 🔶 Partial | 55% | curriculumMapRoutes.js | Prerequisite traversal via gapDetectionEngine; no auto-update on ingest
MasteryScore.js | Per-topic mastery score | ✅ Done | 85% | masteryRoutes.js | Auto-updated after baseline/tutor/practice/practice-paper/exam via masteryEventService
BaselineQuiz.js | Baseline quiz schema | ✅ Done | 90% | baselineRoutes.js | Results feed mastery
BaselineResult.js | Baseline quiz result | 🔶 Partial | 75% | baselineRoutes.js | Wired to mastery update; consumer testing in progress
PracticePaper.js | Practice paper | ✅ Done | 100% | practicePaperRoutes.js | Full CRUD
PracticeQuestion.js | Practice question | 🔶 Partial | 55% | practiceRoutes.js | No Bloom level; not AI-auto-generated
PracticeSection.js | Practice paper section | ✅ Done | 100% | practiceSectionRoutes.js | Full CRUD
PracticeAttempt.js | Practice attempt | 🔶 Partial | 75% | practiceRoutes.js | Feeds mastery via shared assessment writer
TryoutResult.js | AI tryout result | ✅ Done | 90% | aiLearningRoute.js | Feeds mastery
FlashcardResult.js | Flashcard rating result | 🔶 Partial | 45% | — | Ratings persist via applyAssessment; dedicated result rows not used from UI
ExternalResource.js | External study links | ✅ Done | 100% | externalResourceRoutes.js | Full CRUD
SpacedRepetitionSchedule.js | SM-2 review schedule | 🔶 Partial | 65% | spacedRepetitionRoutes.js | SM-2 + cron nudges + recommendation tie-in; not auto-triggered from every result
TeacherLearningPath.js | Teacher learning path | 🔶 Partial | 50% | learningPathRoutes.js | Manual paths; weekly AI study-plan generated separately
StudentProgress.js | Student progress snapshot | 🔶 Partial | 65% | progressRoute.js | Feeds analytics + forecast; reconciliation sweep every 15 min
StudentMemorySummary.js | AI student memory summary | 🔶 Partial | 50% | — | Rolling session-summarise; retention policy incomplete
TutorConversation.js | AI tutor chat session | 🔶 Partial | 55% | aiTutorRoutes.js | Persisted + teacher corrections joined on read; cross-session recall via summary only
ReadingMaterial.js | Reading passage upload | ✅ Done | 100% | readingAssessmentRoutes.js | Full CRUD
ReadingAssessment.js | Reading attempt + scores | ✅ Done | 95% | readingAssessmentRoutes.js | End-to-end pipeline working
WritingPrompt.js | Writing prompt upload | ✅ Done | 100% | writingAssessmentRoutes.js | Full CRUD
WritingAssessment.js | Writing submission + scores | ✅ Done | 95% | writingAssessmentRoutes.js | End-to-end pipeline working
StudentLanguageProfile.js | Adaptive language profile | ✅ Done | 85% | — | Qdrant memory active
── STUDENT WELFARE ─────────────────────────────────────────────────────
StudentBadge.js | Achievement badge | 🔶 Partial | 60% | achievementRoutes.js | masteryEngine award logic; full auto-award UI pending
StudentJournalEntry.js | Personal journal | 🔶 Partial | 40% | — | Model only; no UI
StudentObservation.js | Teacher observation note | 🔶 Partial | 55% | studentObservationRoutes.js | Not linked to intervention
Wellbeing.js | Wellbeing check-in | 🔶 Partial | 40% | wellbeingRoute.js | No safeguard/escalation layer
InterventionLog.js | Teacher intervention record | ✅ Done | 80% | — | Auto follow-up checkpoints + plan templates + automatic improvement + auto-finalize
Behaviour.js | Behaviour incident | ✅ Done | 100% | behaviourRoute.js | Full CRUD
ExcuseLetter.js | Excuse letter submission | ✅ Done | 100% | excuseLetterRoutes.js | Full CRUD
── COMMUNICATION & FINANCE ─────────────────────────────────────────────
ChatThread.js | Real-time chat thread | ✅ Done | 100% | chatRoutes.js | Socket.IO active
ChatMessage.js | Chat message | ✅ Done | 100% | chatRoutes.js | Active
Notification.js | Push notification | ✅ Done | 100% | notificationRoutes.js | Web push + in-app
PushSubscription.js | Browser push sub | ✅ Done | 100% | notificationRoutes.js | VAPID keys active
AlcovePost.js | Academic Alcove post | ✅ Done | 100% | alcoveRoute.js | Full CRUD
AlcoveComment.js | Alcove comment | ✅ Done | 100% | alcoveRoute.js | Full CRUD
AlcoveSubmission.js | Alcove submission | ✅ Done | 100% | alcoveRoute.js | Full CRUD
FeeStructure.js | Fee structure | ✅ Done | 100% | feeRoutes.js | Full CRUD
FeeInvoice.js | Fee invoice | ✅ Done | 100% | feeRoutes.js | Full CRUD
FeePayment.js | Razorpay payment | ✅ Done | 100% | feeRoutes.js | Razorpay integrated
PaymentAudit.js | Payment audit trail | ✅ Done | 100% | paymentSettingsRoutes.js | Full audit log
AuditLog.js | System audit log | ✅ Done | 100% | auditLogRoutes.js | All key events logged
── AI LAYER (added since 2026-08-11) ───────────────────────────────────
MasteryEvent.js | Immutable mastery-change audit | ✅ Done | 90% | masteryRoutes.js | Append-only; source-typed; drives growth + risk reads
MasteryScore history via masteryEventService.js | Transactional score+event writer | ✅ Done | 85% | — | Requires replica set; live verification pending
StudentInsight.js | At-risk / gap / milestone records | ✅ Done | 85% | teacherAnalyticsRoutes.js | Dedupe-key unique index; feeds alerts + plans
WeeklyStudyPlan.js | Persisted weekly study plan | ✅ Done | 80% | weeklyStudyPlanRoutes.js | Generated from mastery + recs; student completion endpoint
GeneratedQuestion.js | AI-generated question bank | ✅ Done | 80% | aiTutorRoutes.js | Teacher save/list/edit/approve; no difficulty calibration
ErrorRecord.js | Per-answer error classification | ✅ Done | 85% | teacherAnalyticsRoutes.js | Concept/Calculation/Reading/Logic; feeds error-breakdown
RecommendationEvent.js | Recommendation lifecycle + impact | ✅ Done | 80% | recommendationRoutes.js | issued→accepted→completed; mastery delta measured; cron finalize
TutorAnswerCorrection.js | Teacher override of an AI answer | ✅ Done | 80% | aiTutorRoutes.js | Separate collection; audited; joined onto student + teacher reads
LongAnswerQuestion.js | Teacher-assigned written question | ✅ Done | 80% | longAnswerAssessmentRoutes.js | Draft→published→closed; class/section/subject targeting; scope-checked
LongAnswerSubmission.js | Student written answer + AI grade + review | ✅ Done | 80% | longAnswerAssessmentRoutes.js | AI evaluator score vs model answer/rubric; needs-review gating; teacher override supersedes
AiInteractionLog.js | AI-service call lineage / audit | ✅ Done | 80% | aiTutorRoutes.js | model+prompt+retrieval+latency+outcome per call; TTL retention; admin query endpoint
EscalationCase.js | Serious-concern escalation to leadership | ✅ Done | 80% | escalationRoutes.js | Auto from wellbeing + at-risk signals; principal + counsellor routing; ack/action/resolve lifecycle; weekly dedupe
AiInteractionLog.js / dataRetentionService | AI data retention + erasure | ✅ Done | 80% | aiTutorRoutes.js | Prune conversations 365d / memory 730d; purge on student exit; admin purge + policy endpoints; interaction-log TTL 180d

## AI Service Modules
EEC ML — AI Service Modules
Module | Responsibility | What It Does | Status | Progress % | Notes / Gaps
── BUILT ──────────────────────────────────────────────────────────────
documents | Document ingestion | OCR → parse → chunk → embed → Qdrant upsert | ✅ Done | 92% | OCR/parse/chunk/embed/upsert + Bloom/outcome/topic tagging on ingest
parser | Text extract + cleaner | PyMuPDF/Tesseract/docx/pptx; strip teacher notes | ✅ Done | 90% | _strip_teacher_notes + injection stripping active
embeddings | Embedding generation | nomic-embed-text → Qdrant | ✅ Done | 95% | Fully wired
retrieval | Semantic retrieval | Qdrant metadata filters: school/class/section/subject/chapter | ✅ Done | 90% | Metadata filters + hybrid BM25+semantic RRF + Bloom-level filter
chat | RAG tutor — all modes | explain/quiz/flashcards/notes/mindmap/summarize/homework_help | ✅ Done | 90% | All modes; file-based prompt library overrides inline MODE_INSTRUCTIONS
quiz | Quiz generation | 5 MCQ per request via RAG | ✅ Done | 82% | Bloom-target passed from mastery; not saved to question bank
flashcards | Flashcard generation | Q:/A: format via RAG | ✅ Done | 85% | Ratings persist to mastery
summaries | Summary generation | Chapter summaries; OCR + summarize endpoint | ✅ Done | 90% | Working well
assessment | Language eval (Qwen3 8B) | Reading + writing rubric + score JSON | ✅ Done | 90% | Reading + writing rubric scoring
speech | Audio transcription | faster-whisper + SpeechBrain pronunciation | ✅ Done | 85% | faster-whisper + wav2vec2 pronunciation
language_memory | Adaptive language memory | Qdrant student_language_memory; store/retrieve | ✅ Done | 82% | Qdrant student_language_memory store/retrieve
admin | Admin module | Admin-facing AI controls | 🔶 Partial | 35% | POST /generate/admin-insights live; broader admin controls pending
── ENGINES — implemented Node-side by design (CLAUDE.md) ──────────────
orchestrator | Central AI coordinator | Node → Orchestrator → engines | ✅ Done | 85% | POST /orchestrate dispatch — generate / generate_questions / evaluate / summarize_session / class_performance
knowledge_graph | Graph traversal | Walk prerequisites; find root-cause weak topics | 🔶 Partial | 40% | Traversal lives in Node (gapDetectionEngine.js) by design; no Python module
bloom | Bloom classifier | Tag documents, questions, answers | ✅ Done | 85% | classifier/bloom.py — tags docs on ingest; question + retrieval integration
mastery_engine | Mastery calculator | accuracy + attempts + time + recency; auto-update | 🔶 Partial | 50% | Lives in Node (masteryEngine + masteryEventService) by design; no Python module
error_classifier | Error type classifier | Concept/Calculation/Reading/Logic | ✅ Done | 80% | ai-service classifier + backend/services/errorClassifier.js
gap_detector | Gap detection | Prerequisite traversal → root-cause weak topic | 🔶 Partial | 60% | Lives in Node (gapDetectionEngine.js) by design; prerequisite traversal + root-cause
recommendation | Recommendation engine | Next topic based on mastery + curriculum graph | 🔶 Partial | 60% | Lives in Node (recommendationEngine.js + impact tracking) by design
analytics | AI analytics insights | Per-topic heatmap; at-risk; AI narrative | 🔶 Partial | 60% | Lives in Node (classLearningAnalytics.js + teacherAnalyticsRoutes) by design; AI narrative via /class-insights
prompt_library | Prompt directory | externalise all prompts from Python modules | ✅ Done | 85% | ai-service/prompts/ + loader.py (~50 files)
── ADDED SINCE 2026-08-11 ─────────────────────────────────────────────
evaluator | MCQ / written answer scoring | POST /evaluate/answer — marks, rubric, missing concepts, confidence | ✅ Done | 80% | Wired to stored exam + rubric-assignment answers
classifier | Bloom / outcomes / topic | bloom.py + outcomes.py + topic.py — imported by documents + chat | ✅ Done | 82% | Runs on ingest; legacy chunks need re-index
stem | Math answer verification | service.py + verifier.py — arithmetic / unit checks | 🔶 Partial | 45% | No step-by-step solver UI, no dedicated math model
vision | Image understanding | POST /vision/explain-image + PDF-page vision on ingest (client.py) | 🔶 Partial | 55% | No student photo-of-problem upload flow

## Summary
EEC ML — Master Progress Summary (2026-09-10)
Domain | Total Features | ✅ Done | 🔶 Partial | ❌ Not Started | Next Action
Core AI Pipeline | 6 | 6 | 0 | 0 | Done — orchestrator, hybrid search, prompt library all live
Content Intelligence | 5 | 3 | 2 | 0 | Re-index legacy chunks for Bloom/outcomes; finish doc-versioning UI
Assessment & Evaluation | 6 | 5 | 1 | 0 | Live replica-set DB verification of the mastery/evaluator pipeline
Mastery & Memory | 6 | 1 | 5 | 0 | Validate forecasts on longitudinal data; academic-memory retention policy
Gap & Learning Path | 4 | 3 | 1 | 0 | Wire recommendation widget to accept/complete; AI bridge-path generation
AI Content Generation (Student) | 9 | 7 | 2 | 0 | Personalise worksheets to mastery gaps; adaptive item selection
AI Content Generation (Teacher) | 4 | 1 | 3 | 0 | Teacher UI for Bloom/difficulty selection; surface override affordance
Language Assessment | 3 | 3 | 0 | 0 | Real-device mic testing; surface language profile card
Analytics & Intelligence | 7 | 3 | 4 | 0 | Teacher dashboard cards for engagement + at-risk; narrative-quality eval
Research-Grade Features | 14 | 1 | 8 | 5 | Safety escalation + safeguarding + explainable-AI lineage
Future Features | 9 | 0 | 5 | 4 | Voice loop, student image upload, math step-solver UI
TOTAL | 73 | 33 | 31 | 9
Overall: 33 Done + 31 Partial + 9 Not Started out of 73 (45% fully done, 88% at least started)
Re-audited 2026-09-10 against the AI-layer build (see AI_UNTOUCHED_FEATURES_CHECKLIST.md)
Core learning-intelligence engines (orchestrator, hybrid search, Bloom, error classifier, gap detection, mastery auto-update, recommendations, study plan) now built; remaining gaps concentrate in safety/governance, quality monitoring, and training-data infra
TOP 5 PRIORITIES (2026-09-10)
1. Safety & governance layer | Wellbeing→human escalation, safeguarding workflow, consent controls, PII redaction
2. AI quality & cost monitoring | Latency / token / cost / version logging; grounding + hallucination measurement
3. Training-data pipeline | Interaction-logging schema, redaction, dataset versioning, model registry + rollback
4. Frontend wiring | Recommendation accept/complete widget, teacher AI-override UI, unified health card
5. Model + prompt version logging | Log which model / prompt / retrieval config produced each AI output (feeds quality + training-data work)