## All AI Features
EEC ML — All AI Features
# | Feature | Status | Progress % | In Old CSV? | Files / Location | What's Missing
── 1. CORE AI PIPELINE ──────────────────────────────────────────────────────────────────────────────────────
1 | Document Ingestion (OCR → Parse → Chunk → Embed → Qdrant) | ✅ Done | 95% | Yes | ai-service/app/modules/documents/ | Bloom + learning-outcome + topic tagging now run on ingest; legacy chunks need re-index
2 | AI Orchestrator (central workflow coordinator) | ✅ Done | 85% | No | NEEDED: ai-service/app/orchestrator/ | POST /orchestrate dispatch live; ingest/OCR/speech/vision still called directly by design
3 | RAG Engine (semantic retrieval with metadata filtering) | ✅ Done | 95% | Yes | ai-service/app/modules/retrieval/ | Hybrid BM25+semantic (RRF) now merged in; fusion weights untuned
4 | Hybrid Search (BM25 keyword + semantic vector) | ✅ Done | 85% | No | NEEDED in retrieval/service.py | Reciprocal-rank-fusion of vector + keyword hits in retrieval/service.py; weight tuning pending
5 | Embedding Engine (nomic-embed-text via Ollama) | ✅ Done | 95% | No | ai-service/app/modules/embeddings/ | Fully wired
6 | Prompt Library (externalised /prompts/ directory) | ✅ Done | 85% | No | NEEDED: ai-service/prompts/ | ai-service/prompts/ + loader.py (~50 files); a few module prompts still inline
── 2. CONTENT INTELLIGENCE ─────────────────────────────────────────────────────────────────────────────────
7 | Curriculum Graph (topic → prerequisite map) | ✅ Done | 85% | Yes | backend/models/CurriculumMap.js + curriculumMapRoutes.js | Section-scoped curriculum maps now auto-sync topics, outcomes, and concepts during ingest; prerequisite authoring remains manual.
8 | Learning Outcomes Auto-generation from documents | ✅ Done | 80% | No | NEEDED in documents/service.py | classifier/outcomes.extract_learning_outcomes runs on ingest; legacy docs need re-index
9 | Bloom Engine (tag documents + questions + answers) | ✅ Done | 85% | No | NEEDED: ai-service/app/modules/bloom/ | classifier/bloom on ingest + retrieval filter + question-gen + mastery progression; legacy chunks need re-index
10 | Document Versioning (retain old versions, never auto-delete) | ✅ Done | 80% | No | NEEDED in TeachingMaterial.js | Remaining: TeachingMaterial.versions[] + isEnabled (disable-not-delete) exist; no auto-version-on-reupload, no version-browse UI
11 | Question Bank (permanent store, teacher-editable) | ✅ Done | 80% | Yes | backend/models/ExamQuestion.js + PracticeQuestion.js | GeneratedQuestion store + teacher save/list/edit/approve APIs; no difficulty calibration
── 3. ASSESSMENT & EVALUATION ─────────────────────────────────────────────────────────────────────────────
12 | Academic Assessment Engine (MCQ + written answer eval) | ✅ Done | 80% | Yes | ai-service/app/modules/assessment/ | MCQ + written + long-answer all evaluated; dedicated long-answer student workflow (LongAnswerQuestion/Submission + /api/long-answer-assessments) now built; live replica-set DB verification pending
13 | Language Reading Assessment (Qwen3 8B scoring) | ✅ Done | 95% | Yes | ai-service + ReadingAssessment.js + ReadingPracticePage.jsx | End-to-end pipeline working
14 | Language Writing Assessment (Qwen3 8B scoring) | ✅ Done | 95% | Yes | ai-service + WritingAssessment.js + WritingPracticePage.jsx | End-to-end pipeline working
15 | Answer Evaluator — full rubric (marks/rubric/Bloom/confidence/missing concepts/mastery update) | ✅ Done | 90% | No | ai-service/app/modules/assessment/service.py | Remaining: Marks/rubric/Bloom/confidence/missing-concepts persisted on exam + assignment + long-answer submissions; needs-review gating + teacher-override supersede wired
16 | Error Classification Engine (Concept/Calculation/Reading/Logic) | ✅ Done | 85% | Yes | NEEDED: ai-service/app/modules/error_classifier/ | backend/services/errorClassifier.js + ai-service classifier — Concept/Calculation/Reading/Logic all classified
17 | Baseline Quiz (initial mastery estimate) | ✅ Done | 90% | Yes | backend/models/BaselineQuiz.js + BaselineQuiz.jsx | Results feed mastery via masteryEventService
── 4. MASTERY & MEMORY ─────────────────────────────────────────────────────────────────────────────────────
18 | Mastery Engine (score calculate + auto-update after every attempt) | ✅ Done | 85% | Yes | backend/services/masteryEngine.js + MasteryScore.js | Auto-update across baseline/tutor/practice/practice-paper/exam + immutable MasteryEvent history; replica-set txns + live verification pending
19 | ML Engine (weighted EMA mastery, at-risk detection, class trends) | ✅ Done | 90% | No | backend/services/mlEngine.js + mlRoutes.js + mlValidationService.js | Event-stream EMA + attendance-aware risk bands live. Retrospective backtest harness (mlValidationService.js + GET /api/ml/class/at-risk-validation) now measures real precision/recall/F1 by predicting at-risk status as of a cutoff and checking each student's own later assessments as ground truth — needs no external data. Remaining: numbers become statistically meaningful once enough longitudinal history accumulates per school (flagged as insufficient_sample below 10 students).
20 | Engagement Scorer (time × views × attempts per topic) | ✅ Done | 75% | No | backend/services/engagementScorer.js + engagementRoutes.js | Per-student views, time, quiz attempts, and three engagement dimensions are scored; teacher dashboard card pending.
21 | Spaced Repetition Engine (SM-2 algorithm, review scheduling) | ✅ Done | 85% | No | backend/models/SpacedRepetitionSchedule.js + spacedRepetitionRoutes.js | SM-2 scheduling is triggered after mastery events and surfaced through due/all APIs; review UX polish remains.
22 | Student Academic Memory (weak topics, past mistakes, study history) | ✅ Done | 80% | No | NEEDED: extend StudentMemorySummary.js | Remaining: StudentMemorySummary + /academic-memory endpoint; summarisation pipeline partial, retention policy incomplete
23 | Conversation Memory (persisted cross-session) | ✅ Done | 80% | No | TutorConversation.js exists; no cross-session recall | Remaining: TutorConversation persisted + rolling session-summarise into long-term memory; retention/lifecycle policy incomplete
── 5. GAP DETECTION & LEARNING PATH ───────────────────────────────────────────────────────────────────────
24 | Gap Detection Engine (traverse graph → root-cause weak topics) | ✅ Done | 80% | Yes | NEEDED: ai-service/app/modules/gap_detector/ | gapDetectionEngine.js — prerequisite traversal + root-cause weak-topic detection; depends on error-classifier signal quality
25 | Recommendation Engine (next topic + material based on mastery) | ✅ Done | 80% | No | backend/routes/recommendationRoutes.js | recommendationEngine.js + acceptance/completion/impact tracking (RecommendationEvent); frontend widget wiring pending
26 | AI-generated Learning Path (bridge from gap → target topic) | ✅ Done | 80% | Yes | NEEDED in ai-service; TeacherLearningPath.js exists for manual | learningPathService.buildBridgePath — curriculum-graph traversal from root-cause gap to a target topic, mastery-aware node states; POST/GET /api/learning-paths/bridge. Tests: learningPathService.test.js
27 | Personalised Study Plan (week-by-week schedule output) | ✅ Done | 80% | Yes | NEEDED: integrate gap → path → study plan generator | weeklyStudyPlanService + WeeklyStudyPlan + GET/PATCH /api/study-plans/*; no calendar export
── 6. AI CONTENT GENERATION (Student) ─────────────────────────────────────────────────────────────────────
28 | AI Tutor Chat — Explain Mode | ✅ Done | 92% | No | ai-service/app/modules/chat/ (mode=explain) | Mode works
29 | AI Tutor Chat — Homework Help (Socratic) | ✅ Done | 95% | Yes | ai-service/app/modules/chat/ (mode=homework_help) | 7-rule Socratic enforcement active
30 | AI Tutor Chat — Summarize Mode | ✅ Done | 92% | Yes | ai-service/app/modules/summaries/ | Works well
31 | AI Tutor Chat — Notes Mode | ✅ Done | 92% | Yes | ai-service/app/modules/chat/ (mode=notes) | POST /save-note + GET /saved-notes added
32 | AI Tutor Chat — Quiz Mode | ✅ Done | 90% | Yes | ai-service/app/modules/quiz/ + QuizUI | Quiz results not yet auto-saved to Question Bank
33 | AI Tutor Chat — Flashcard Mode | ✅ Done | 92% | Yes | ai-service/app/modules/flashcards/ + FlashcardUI | flashcard-rating persists to mastery via applyAssessment
34 | AI Tutor Chat — Mind Map Mode | ✅ Done | 90% | Yes | ai-service/app/modules/chat/ (mode=mind_map) + MindMapUI | No PDF/image export
35 | Worksheet / Homework Generation (personalised to mastery gaps) | ✅ Done | 80% | No | NEEDED in ai-service chat module | POST /api/ai-teacher/worksheet/personalised — gap profile (weak topics + root causes + dominant error type) targets the worksheet. Tests: personalisedContent.test.js
36 | Adaptive Difficulty (adjust question hardness based on mastery) | ✅ Done | 80% | No | NEEDED: wire MasteryScore into quiz/question generation | adaptiveDifficultyService — within-session step ladder (up on correct run / fast answer, down on wrong), bounded easy..hard, resumes from persisted rung; /api/practice/adaptive/*. Tests: adaptiveDifficulty.test.js
── 7. AI CONTENT GENERATION (Teacher) ─────────────────────────────────────────────────────────────────────
37 | AI Lesson Content Generator (teacher-facing) | ✅ Done | 80% | No | backend/routes/aiTeacherRoutes.js (mode=lesson-content) | Remaining: aiTeacherRoutes lesson-content + prompts/evaluation/lesson_content.txt
38 | AI Hinge Question Generator (teacher-facing) | ✅ Done | 80% | No | backend/routes/aiTeacherRoutes.js (mode=hinge-questions) | Remaining: aiTeacherRoutes hinge-questions + prompts/question_generation/hinge_question.txt
39 | AI Question Paper Generator (teacher selects topic + Bloom) | ✅ Done | 90% | No | backend/routes/aiTeacherRoutes.js (quiz-generate) + PracticePaperBuilder.jsx | Backend now accepts a validated bloomLevel param, injects a Bloom-specific instruction into the generation prompt, and passes it to retrieval for bloom-tagged chunk filtering. PracticePaperBuilder.jsx has a teacher-facing Bloom level picker (generation default + per-question override), persisted on PracticePaper.questions[].bloomLevel. Remaining: formal Exam creation (mockExamRoutes.js) still has no AI-generation entry point — only practice papers are wired to the generator.
40 | Teacher AI Override (correct/edit an AI answer) | ✅ Done | 80% | No | NEEDED: teacher annotation layer | POST/DELETE /api/ai-tutor/teacher/correct-answer + GET /teacher/corrections; audited, allocation-scoped, joined onto reads. Frontend affordance pending
── 8. LANGUAGE ASSESSMENT ─────────────────────────────────────────────────────────────────────────────────
41 | Speech Transcription (faster-whisper) | ✅ Done | 85% | Yes | ai-service/app/modules/speech/service.py | faster-whisper large-v3-turbo; slow-hardware latency untested
42 | Pronunciation Scoring (SpeechBrain) | ✅ Done | 85% | Yes | ai-service/app/modules/speech/pronunciation.py | wav2vec2 pronunciation scoring; real-device mic testing pending
43 | Student Language Profile (adaptive Qdrant memory) | ✅ Done | 82% | Yes | StudentLanguageProfile.js + language_memory module | Qdrant memory active; not surfaced as a student dashboard card
── 9. ANALYTICS & INTELLIGENCE ────────────────────────────────────────────────────────────────────────────
44 | Teacher Analytics Dashboard (class performance) | ✅ Done | 85% | Yes | teacherAnalyticsRoutes.js | Remaining: At-risk list + risk scores + mastery heatmap + gap results + Bloom distribution; analytics authz hardened; live DB verification + polish pending
45 | Admin Analytics Dashboard (school-level AI metrics) | ✅ Done | 80% | Yes | adminAnalyticsRoutes.js | Remaining: Admin AI performance insights live; subject weak-area report pending
46 | Student Progress Dashboard (unified mastery + gaps + path) | ✅ Done | 75% | Yes | MasteryView.jsx + LearningPathMapView.jsx | Unified GET /health-card (mastery + gaps + SR + language + recs); frontend still shows independent views
47 | At-risk Student Detection (ML engine flag) | ✅ Done | 80% | No | backend/services/mlEngine.js (GET /class/at-risk) | Weak/at-risk list + attendance+assessment+trend scoring + scheduled scans + real-time alerts; forecast validation pending
48 | Class Engagement Analytics (per-topic engagement scores) | ✅ Done | 70% | No | backend/services/engagementScorer.js + engagementRoutes.js | Per-topic engagement endpoint now returns behavioural, situational, and emotional dimensions; teacher card pending.
49 | AI-generated Insights for Teacher ('Class struggles with X') | ✅ Done | 75% | No | NEEDED: LLM summarise analytics data | classLearningAnalytics + /class-insights LLM narrative over real mastery data; narrative-quality eval pending
50 | Wellbeing Tracking (student check-in + admin visibility) | ✅ Done | 75% | No | backend/models/Wellbeing.js + wellbeingRoute.js | Remaining: Model + CRUD + assessment; no human-escalation/safeguard workflow (see Safety)
── 10. RESEARCH-GRADE FEATURES (from Area to Cover doc) ───────────────────────────────────────────────────
51 | Learner Confidence Tracking (dynamic self-perception) | 🔶 Partial | 80% | No | backend/models/StudentConfidenceCheckin.js + confidenceTrackingService.js + confidenceRoutes.js + inline QuizUI in AITutorHomeScreen.jsx | Confidence check-in live in the post-quiz flow; self-rating (1-5) compared against the student's real mastery score to compute a calibration gap (overconfident/underconfident/calibrated). Teacher-facing Confidence tab (StudentAnalyticsPortal) now renders GET /api/confidence/class, ranking most-miscalibrated students first with a class-wide over/under/calibrated stat strip. Student-facing Confidence Calibration card (DashboardHome) now renders GET /api/confidence/profile, showing per-topic calibration labels. Tests: confidenceTrackingService.test.js. Remaining: check-ins only fire after quiz mode (practice/homework modes not wired).
52 | Help-Seeking Behaviour (log when/how student asks for help) | 🔶 Partial | 55% | No | backend/models/HelpSeekingEvent.js + helpSeekingService.js + helpSeekingRoutes.js + aiTutorRoutes.js hook + StudentAnalyticsPortal Help-Seeking tab | Backend-observed signal: every Homework Help turn is logged automatically (no extra frontend instrumentation needed), plus a regex-based 'stuck' detector on the student's own message text ("I don't know", "idk", "I'm stuck", etc). Teacher-facing Help-Seeking tab ranks students by frequency, most-active first. Tests: helpSeekingService.test.js. Remaining: only Homework Help mode is instrumented — quiz retries, hint clicks in other modes, and give-up signals elsewhere are not yet tracked; no student-facing view of their own pattern.
53 | Retention / Forgetting Model (knowledge decay over time) | ✅ Done | 90% | No | SpacedRepetitionSchedule.js + spacedRepetitionRoutes.js + ForgettingCurveChart in DashboardHome.jsx | Retention estimate + fading/at-risk status via /api/spaced-repetition/retention, now visualized as a real decay curve (ForgettingCurveChart, same exponential formula as the backend) for the 3 most at-risk topics on the student dashboard. Remaining: curve is client-side projected from the snapshot endpoint rather than a backend-returned point series — cosmetic, not a data gap.
54 | Misconceptions Engine (explicit error model per topic/student) | ✅ Done | 80% | No | NEEDED: extend error classifier output | StudentMisconception — recurring same-type errors auto-rolled per topic (capped evidence), auto-resolved at mastery >= 75; GET /api/teacher-analytics/student-misconceptions/:id. Tests: misconceptionService.test.js
55 | Multidimensional Engagement (situational + behavioural + emotional) | ✅ Done | 90% | No | engagementScorer.js + mlEngine.js (computeEngagement) + StudentAnalyticsPortal.jsx (MLStudentDetailModal) | Behavioural + situational + emotional dimensions computed and now rendered as progress bars in the teacher-facing student detail modal. Remaining: no student-facing view of their own engagement yet.
56 | Intervention Effectiveness (measure what actually improves learning) | ✅ Done | 75% | No | NEEDED: analytics overlay on interventions | Auto follow-up plans + 7/14/30-day checkpoints + automatic improvement calc + auto-finalize; escalation to leadership + longitudinal validation pending
57 | Teacher Escalation (auto-flag students for human support) | ✅ Done | 80% | No | NEEDED: alert system from gap detection / at-risk engine | Remaining: Automatic deduplicated intervention-plan creation on at-risk alert; counsellor/leadership escalation not built
58 | Student Agency (learner control over learning path) | 🔶 Partial | 60% | No | recommendationRoutes.js + RecommendationWidget.jsx + learningPathRoutes.js (bridge) + LearningPathMapView.jsx | Recommendation accept/dismiss now wired end-to-end: RecommendationWidget.jsx calls POST /api/recommendations/:id/:decision on every click, recording real student choices instead of only inferring intent from click-through. Remaining: true path branching/selection — the learning-path backend is strictly linear (mark active node done, unlock next); a student still cannot choose between alternative paths or preview/adopt a bridge path themselves.
59 | Explainable AI (why did AI recommend / answer this?) | ✅ Done | 95% | No | aiInteractionLogger.js + AiInteractionLog.js + admin audit endpoint + TutorReasoningTrace.jsx in AITutorHomeScreen.jsx | The lineage block (model, retrieval query, chunk/citation counts) was already computed and returned by the backend but silently dropped on the frontend — now wired through message state and shown via a new "Why this answer?" disclosure, alongside the non-visual source list. Remaining: none identified; polish only.
60 | Social / Belonging Dimension (peer signals + community) | 🔶 Partial | 50% | No | backend/services/belongingService.js + belongingRoutes.js + DashboardHome BelongingCard | Belonging score computed from Alcove peer-community activity (posts, comments, likes given/received), banded isolated/low/moderate/active. Student-facing Community card on DashboardHome. Teacher-facing getClassBelongingSummary() exists and is tested but has no consuming UI yet. Tests: belongingService.test.js. Remaining: teacher dashboard view; likes given/received are all-time (AlcovePost.likedBy has no per-like timestamp) rather than windowed like posts/comments.
61 | Evidence Testing (prove platform improves learning outcomes) | ✅ Done | 75% | No | NEEDED: pre/post measurement framework | OutcomeStudy + outcomeStudyService — pre/post window capture from MasteryEvent, paired mean delta + %-improved + Cohen-d effect size; /api/teacher-analytics/outcome-studies/*. Tests: outcomeStudy.test.js
62 | Equity / Bias Monitoring (detect uneven model performance) | 🔶 Partial | 40% | No | backend/services/equityMonitoringService.js + GET /api/admin-analytics/equity-monitoring | Deliberately scoped to gender only — caste/religion/category exist on StudentUser but are NOT used; slicing AI performance by those fields needs dedicated ethical review and is out of scope for an automated monitor (see service file header). Compares the AI answer evaluator's avg score and needs-review rate across gender cohorts (min sample size gated) and flags large gaps as a prompt for human review, never a verdict. Tests: equityMonitoringService.test.js. Remaining: no admin UI yet (backend/API only); cohort scope could later extend to class/section.
63 | Wellbeing Safeguards (child protection + human support boundary) | ✅ Done | 85% | No | backend/models/EscalationCase.js + escalationService.js + escalationRoutes.js + wellbeingController.js | Already fully built in an earlier pass — this row was simply never updated. Every wellbeing check-in save runs escalateWellbeingIfNeeded(): a 'critical' mood or a 'concerning' mood combined with behaviour changes/high stress/low social score auto-raises a deduplicated (one open case per student/category/ISO-week) EscalationCase, routed to principals + counselling/welfare staff with a notification and audit log entry. escalationRoutes.js gives leadership raise/acknowledge/resolve endpoints. Tests: escalation.test.js, escalationRoutes.test.js. Remaining: no dedicated safeguard-case dashboard UI beyond the generic escalation views.
64 | AI / Data Ethics Framework (child-centered, beyond RBAC) | ✅ Done | 75% | No | JWT + RBAC + tenant isolation done | aiConsentService — AI personalisation gated on parentConsentGivenAt (per-org overridable, fails safe); /generate omits personal-data prompt without consent + reports personalisationApplied; admin consent endpoint + audit. Tests: aiConsent.test.js
── 11. FUTURE FEATURES (Architecture doc roadmap) ─────────────────────────────────────────────────────────
65 | Voice Tutor (speech-to-text + AI response + TTS) | ✅ Done | 85% | No | AITutorHomeScreen.jsx (Web Speech API mic input, already existed) + new auto-speak/Listen TTS (browser SpeechSynthesis) | Speech-to-text input already existed (browser SpeechRecognition mic button sets the composer text) but the loop stopped there. Added the missing half: a per-message 'Listen' button plus an auto-speak toggle that reads the tutor's answer aloud via the browser's native SpeechSynthesis as soon as it finishes streaming — markdown/LaTeX/code-fence markup is stripped before speaking. No new backend or model needed; both halves are native browser APIs. Remaining: voice is not tied per-turn to 'this answer was to a voice question' (auto-speak is a session-wide toggle); no server-side TTS voice selection.
66 | Image Understanding (student uploads photo of problem) | ✅ Done | 80% | No | NEEDED: vision model integration (LLaVA/Qwen-VL) | POST /api/ai-tutor/explain-photo — student photo (Cloudinary URL, SSRF-guarded) downloaded + base64 -> /vision/explain-image; logged as AI interaction. Tests: explainPhoto.test.js
67 | Video Understanding (lecture video → summary + quiz) | ✅ Done | 75% | No | ai-service app/modules/video/ (router+service+schemas) + backend/routes/videoUnderstandingRoutes.js + frontend/src/teachers/VideoUnderstandingTool.jsx | Audio-only pipeline: faster-whisper decodes audio via ffmpeg regardless of container, so a video file is handed to the existing transcription path unchanged — no new model or binary dependency. Transcript -> summarize_text() (factored out of the PDF-summary path) -> a plain-text quiz in the same numbered A-D format the tutor's quiz mode already produces. Teacher uploads a video (reuses /api/uploads/cloudinary/single) and sees transcript + summary + keywords + quiz. Tests: test_video_service.py. Remaining: no frame/vision analysis, so silent slides or on-screen-only text are missed; quiz renders as plain text rather than the interactive QuizUI component.
68 | Code Tutor (programming support + code review) | ✅ Done | 80% | No | ai-service chat/service.py MODE_INSTRUCTIONS["code_help"] + llm.py MODE_TEMPERATURE + AITutorHomeScreen.jsx Code Help chip | New tutor mode: prompt-only code review/explanation (line-level bug analysis, beginner-friendly term definitions, fenced code blocks with language tags) — never claims to execute code. Reuses the tutor's existing generic fenced-code-block renderer unchanged (already handled ```python etc., just never had a mode that produced them intentionally). Tests: ai-service test_chat_service.py (75 passing). Remaining: no execution sandbox — deliberately not built without a security/infra decision, same pattern as the Math Solver's deferred dedicated model.
69 | Math Solver (step-by-step equation solving) | 🔶 Partial | 55% | No | stem/verifier.py + STEM_INSTRUCTIONS (chat/service.py) + TutorMessageContent.jsx (KaTeX) | Step-by-step math prompting already existed via STEM_INSTRUCTIONS + the general tutor model; verifier.py remains answer-only verification (sympy/AST, not step generation). Real math typesetting now added — KaTeX wired into TutorMessageContent.jsx (inline + block, safe fallback to plain text on invalid LaTeX); previously all notation rendered as plain monospace text. Remaining: no dedicated math model (e.g. Qwen-Math) — deliberately not wired in without a product/infra decision (new Ollama model pull, latency/memory testing); a dedicated step-by-step solver UI distinct from generic tutor chat is also still unbuilt.
70 | Topic Failure Prediction (predict fail before test happens) | ✅ Done | 85% | No | classLearningAnalytics.js (forecastClass) + /api/teacher-analytics/at-risk-7day (live in StudentAnalyticsPortal.jsx) + forecastValidationService.js | forecastScores-based 7-day-ahead forecast was already surfaced in the teacher UI (StudentAnalyticsPortal.jsx) — not dead code. New forecastValidationService.js backtests the pass/fail prediction against each student's own following week as ground truth (confusion matrix), via GET /api/teacher-analytics/forecast-validation. Tests: forecastValidationService.test.js. Remaining: needs real longitudinal history to accumulate before results are statistically meaningful (insufficient_sample gate below 10 students, same pattern as the at-risk backtest).
71 | Learning Style Detection (visual/reading/quiz preference) | 🔶 Partial | 55% | No | backend/services/learningStyleService.js + learningStyleRoutes.js + DashboardHome LearningStyleCard | Detects the dominant content-format category (visual/reading/hands-on/listening) from the student's own AiInteractionLog tutor-mode history and compares it against the self-reported StudentUser.learningPreferences.learningStyle field collected at onboarding, flagging agreement or mismatch. Student-facing card on DashboardHome. getClassLearningStyleSummary() (class distribution) exists and is tested but has no teacher-facing UI yet. Tests: learningStyleService.test.js. Remaining: teacher dashboard view; style buckets are a simple mode-frequency heuristic, not genuine interaction-pattern clustering.
72 | Performance Forecasting (predicted score on next test) | ✅ Done | 85% | Yes | learningEvidenceService.js (forecastScores) + classLearningAnalytics.js + forecastValidationService.js | Daily least-squares score forecast + class forecast already live. forecastValidationService.js now backtests regression accuracy (MAE/RMSE) against each student's own actual score the following week — no external cohort data needed. Tests: forecastValidationService.test.js. Remaining: same data-accumulation caveat — MAE/RMSE become meaningful once enough real history exists per school.
73 | At-risk / Dropout Risk Prediction (ML model) | ✅ Done | 90% | Yes | mlEngine.js (computeAtRisk / dropoutRisk) + mlValidationService.js | Same computeAtRisk/dropoutRisk logic tracked under #19 (ML Engine) — already validated by mlValidationService.js's retrospective backtest (precision/recall/F1 against each student's own later assessments). "Dedicated trained model" was a design choice, not a gap: an interpretable rule-based band (attendance + mastery + trend) was chosen over a black-box model for explainability to teachers. Remaining: same data-accumulation caveat as above.

## Missing from Old CSV
EEC ML — Features Missing from Old CSV Checklist
Feature | Status | Progress % | Files / Location | Why It Was Missing
── ALREADY BUILT — but not in the old checklist ────────────────────────
Embedding Engine | ✅ Done | 95% | ai-service/app/modules/embeddings/ | Fully wired
Explain Mode (AI Tutor) | ✅ Done | 92% | ai-service chat module (mode=explain) | Mode works
ML Engine (EMA mastery) | 🔶 Partial | 90% | backend/services/mlEngine.js | Event-stream EMA reader is live; retrospective forecast backtest (forecastValidationService.js) now validates it against each student's own later results and is surfaced as accuracy/precision/recall/MAE stats in the teacher 7-Day Forecast tab.
Engagement Scorer | ✅ Done | 75% | backend/services/engagementScorer.js | Per-student behavioural + situational + emotional scoring is live; teacher card pending.
Spaced Repetition (SM-2) | 🔶 Partial | 65% | backend/models/SpacedRepetitionSchedule.js | SM-2 + cron + recommendation tie-in
Recommendation Engine | ✅ Done | 80% | backend/routes/recommendationRoutes.js | Engine + acceptance/completion/impact tracking; frontend wiring pending
At-risk Student Detection | ✅ Done | 80% | backend/routes/mlRoutes.js (GET /class/at-risk) | Scheduled scans + real-time alerts + StudentInsight record
Engagement Analytics | 🔶 Partial | 45% | backend/routes/engagementRoutes.js | Endpoint live; no teacher card
AI Lesson Content (Teacher) | 🔶 Partial | 55% | backend/routes/aiTeacherRoutes.js (lesson-content) | Route + externalised prompt
AI Hinge Question (Teacher) | 🔶 Partial | 55% | backend/routes/aiTeacherRoutes.js (hinge-questions) | Route + externalised prompt
Wellbeing Tracking | 🔶 Partial | 40% | backend/models/Wellbeing.js + wellbeingRoute.js | Model + CRUD; no safeguard/escalation layer
Answer Evaluator (full) | 🔶 Partial | 75% | ai-service/app/modules/assessment/ | Missing-concept + confidence persisted on exam + assignment + long-answer; needs-review gating
── ARCHITECTURAL — not in old checklist ────────────────────────────────
AI Orchestrator | ✅ Done | 85% | NEEDED: ai-service/app/orchestrator/ | ai-service/app/modules/orchestrator/ — POST /orchestrate dispatch
Prompt Library | ✅ Done | 85% | NEEDED: ai-service/prompts/ | ai-service/prompts/ + loader.py (~50 files)
Hybrid Search (BM25+vector) | ✅ Done | 85% | NEEDED in retrieval/service.py | RRF fusion of vector + keyword hits in retrieval/service.py
Document Versioning | 🔶 Partial | 60% | NEEDED in TeachingMaterial.js | TeachingMaterial.versions[] + isEnabled; no auto-version-on-reupload / browse UI
Learning Outcomes Auto-gen | ✅ Done | 80% | NEEDED in documents/service.py | classifier/outcomes on ingest; legacy docs need re-index
Bloom Engine | ✅ Done | 85% | NEEDED: ai-service/app/modules/bloom/ | classifier/bloom on ingest + retrieval filter + question-gen + mastery progression
── CONTENT GENERATION — not in old checklist ──────────────────────────
Worksheet / Homework Gen | 🔶 Partial | 50% | NEEDED in chat module | POST /api/ai-teacher/worksheet; not personalised to mastery gaps
Adaptive Difficulty | 🔶 Partial | 60% | NEEDED: wire MasteryScore → content generation | Mastery→Bloom band drives difficulty; no full adaptive item selection
AI Question Paper (Teacher) | 🔶 Partial | 55% | NEEDED: Bloom + difficulty param in exam gen | Bloom-level question gen exists; teacher selection UI pending
Teacher AI Override | ✅ Done | 80% | NEEDED: annotation layer on AI responses | correct-answer + withdraw + list endpoints; audited + allocation-scoped; frontend pending
── RESEARCH-GRADE — not in old checklist ──────────────────────────────
Learner Confidence | 🔶 Partial | 80% | backend/models/StudentConfidenceCheckin.js + confidenceTrackingService.js + confidenceRoutes.js + QuizUI check-in + DashboardHome + StudentAnalyticsPortal Confidence tab | Post-quiz check-in, calibration-gap scoring, student calibration card, and teacher class dashboard all live and tested. Remaining: practice/homework-mode check-ins.
Help-Seeking Behaviour | 🔶 Partial | 55% | HelpSeekingEvent.js + helpSeekingService.js + helpSeekingRoutes.js | Homework Help turns + "I don't know"-style signals logged automatically; teacher-facing ranked tab. Remaining: only Homework Help mode instrumented.
Misconceptions Engine | 🔶 Partial | 45% | NEEDED: extend error classifier | Class-wide aggregation + tutor mode; per-student model pending
Multidimensional Engagement | 🔶 Partial | 75% | engagementScorer.js (behavioural + situational + emotional) + StudentAnalyticsPortal dimension bars | Situational + emotional dimensions now computed in engagementScorer.js and rendered per-student (behavioural/situational/emotional bars) in the teacher ML Insights detail modal. Remaining: no class-wide aggregate card.
Intervention Effectiveness | ✅ Done | 75% | NEEDED: analytics on interventions | Auto follow-up + 7/14/30-day checkpoints + automatic improvement calc + auto-finalize
Teacher Escalation | 🔶 Partial | 35% | NEEDED: alert from gap/at-risk engine | Auto intervention-plan creation on alert; counsellor/leadership escalation not built
Student Agency | 🔶 Partial | 60% | recommendationRoutes.js + RecommendationWidget.jsx + learningPathRoutes.js (bridge) | Accept/dismiss recorded end-to-end: RecommendationWidget.jsx calls POST /api/recommendations/:id/:decision on every click (tested). Remaining: no path-selection UI — learning-path backend is strictly linear.
Explainable AI | 🔶 Partial | 80% | aiInteractionLogger.js + AiInteractionLog.js (lineage) + TutorReasoningTrace.jsx | Reasoning-trace lineage (model, mode, prompt source, retrieval chunk/citation counts, rewritten search query) plus grounding source materials are now surfaced in the tutor UI via a collapsible "Why this answer?" panel (TutorReasoningTrace.jsx, tested). Explainability string on recommendations unchanged.
Social / Belonging | 🔶 Partial | 50% | belongingService.js + belongingRoutes.js + DashboardHome BelongingCard | Belonging score from Alcove posts/comments/likes, student card live. Remaining: no teacher-facing view yet.
Evidence Testing | 🔶 Partial | 25% | NEEDED: pre/post outcome measurement | Evidence summaries + forecast infra; no pre/post framework
Equity / Bias Monitoring | 🔶 Partial | 40% | equityMonitoringService.js + GET /api/admin-analytics/equity-monitoring | Gender-cohort AI evaluator parity check (score gap + needs-review gap), deliberately excludes caste/religion. Remaining: no admin UI yet.
Wellbeing Safeguards | ✅ Done | 85% | EscalationCase.js + escalationService.js + escalationRoutes.js + wellbeingController.js | Already fully built — row was simply never updated. Auto-escalates distressed wellbeing check-ins to principals/counsellors, deduplicated + audited.
AI / Data Ethics Framework | 🔶 Partial | 20% | JWT + RBAC + tenant isolation done | RBAC + tenant isolation; no child-ethics/consent framework
── FUTURE — not in old checklist ──────────────────────────────────────
Voice Tutor | ✅ Done | 85% | AITutorHomeScreen.jsx (existing Web Speech mic input) + new auto-speak/Listen TTS | STT input already existed; added the missing TTS output half (browser SpeechSynthesis) to close the loop.
Image Understanding | 🔶 Partial | 50% | NEEDED: vision model (LLaVA/Qwen-VL) | vision module + explain-image + PDF-page vision + visual_explain mode; student upload flow pending
Video Understanding | ✅ Done | 75% | ai-service app/modules/video/ + videoUnderstandingRoutes.js + VideoUnderstandingTool.jsx | Audio-only: faster-whisper decodes video containers via ffmpeg unchanged. Transcript -> summary + quiz, teacher upload UI. Remaining: no frame/vision analysis.
Code Tutor | ✅ Done | 80% | chat/service.py MODE_INSTRUCTIONS["code_help"] + Code Help chip in AITutorHomeScreen.jsx | Prompt-only code review/explain mode; reuses existing fenced-code-block renderer. Remaining: no execution sandbox (deliberate).
Math Solver | 🔶 Partial | 40% | NEEDED: math model (Qwen-Math) | stem/verifier.py math-answer verification; step-by-step UI + math model pending
Topic Failure Prediction | 🔶 Partial | 60% | learningEvidenceService.js (forecastScores) + forecastValidationService.js + teacher-analytics forecast-validation route | forecastScores now backtested against each student's own later assessments (retrospective holdout) and surfaced as accuracy/precision/recall/MAE stats in the teacher 7-Day Forecast tab. Remaining: not surfaced to students directly.
Learning Style Detection | 🔶 Partial | 55% | learningStyleService.js + learningStyleRoutes.js + DashboardHome LearningStyleCard | Detects dominant style from AiInteractionLog mode history, compared to self-report. Remaining: no teacher-facing distribution view.

## Backend Models
EEC ML — Backend Models
Model File | Purpose | Status | Progress % | Route File | Notes / Gaps
── AUTH & USERS ─────────────────────────────────────────────────────────
Admin.js | Admin user schema | ✅ Done | 100% | adminRoutes.js | Full CRUD + RBAC
ParentUser.js | Parent account | ✅ Done | 100% | parentRoute.js | Full portal
Principal.js | Principal account | ✅ Done | 100% | principalRoutes.js | Full portal
StaffUser.js | Non-teaching staff | ✅ Done | 100% | staffRoutes.js | Full portal
StudentUser.js | Student account | ✅ Done | 100% | studentRoute.js | Full portal
TeacherUser.js | Teacher account | ✅ Done | 100% | teacherRoute.js | Full portal
SuperAdminActivity.js | Super-admin audit log | ✅ Done | 100% | superAdminRoutes.js | Audit trail
── SCHOOL STRUCTURE ────────────────────────────────────────────────────
Organization.js | Top-level tenant | ✅ Done | 100% | organizationRoutes.js | Multi-tenant root
School.js | School entity | ✅ Done | 100% | schoolRoutes.js | Full CRUD
AcademicYear.js | Academic year | ✅ Done | 100% | academicRoutes.js | Full CRUD
Class.js | Class / grade | ✅ Done | 100% | academicRoutes.js | Full CRUD
Section.js | Section in class | ✅ Done | 100% | academicRoutes.js | Full CRUD
Subject.js | Subject entity | ✅ Done | 100% | subjectRoute.js | Full CRUD
Department.js | Teacher department | ✅ Done | 100% | departmentRoutes.js | Full CRUD
Timetable.js | Class timetable | ✅ Done | 100% | timetableRoutes.js | Full CRUD
Building.js | Campus building | ✅ Done | 100% | — | Reference data
Floor.js | Floor in building | ✅ Done | 100% | — | Reference data
Room.js | Classroom entity | ✅ Done | 100% | — | Reference data
Holiday.js | Holiday calendar | ✅ Done | 100% | holidayRoutes.js | Full CRUD
TeacherAllocation.js | Teacher → class-subject | ✅ Done | 100% | teacherAllocationRoutes.js | Full CRUD
── ACADEMIC & EXAMS ────────────────────────────────────────────────────
Assignment.js | Assignment + submissions | ✅ Done | 100% | assignmentRoute.js | Full CRUD
Exam.js | Exam entity | ✅ Done | 100% | examRoute.js | Full CRUD
ExamAttempt.js | Student exam attempt | ✅ Done | 100% | examRoute.js | Recorded
ExamGroup.js | Exam grouping | ✅ Done | 100% | examRoute.js | Full CRUD
ExamQuestion.js | MCQ/short/long question | 🔶 Partial | 60% | examRoute.js | Evaluator wired for written answers; no Bloom/difficulty calibration
ExamResult.js | Exam result record | ✅ Done | 100% | examRoute.js | Full CRUD
LessonPlan.js | Teacher lesson plan | ✅ Done | 100% | lessonPlanRoutes.js | Full CRUD
LessonPlanCompletion.js | Lesson completion track | ✅ Done | 100% | lessonPlanRoutes.js | Tracked
ReportCardTemplate.js | Report card template | ✅ Done | 100% | reportRoutes.js | Full CRUD
TeachingMaterial.js | Teacher-uploaded material | ✅ Done | 100% | teachingMaterialRoutes.js | Cloudinary + Qdrant ingest
Rubric.js | Grading rubric | 🔶 Partial | 70% | rubricRoutes.js | Rubric assignments now use the AI evaluator
PromotionHistory.js | Student promotion record | ✅ Done | 100% | promotionRoutes.js | Full CRUD
── AI & LEARNING ───────────────────────────────────────────────────────
CurriculumMap.js | Topic prerequisite graph | 🔶 Partial | 55% | curriculumMapRoutes.js | Prerequisite traversal via gapDetectionEngine; no auto-update on ingest
MasteryScore.js | Per-topic mastery score | ✅ Done | 85% | masteryRoutes.js | Auto-updated after baseline/tutor/practice/practice-paper/exam via masteryEventService
BaselineQuiz.js | Baseline quiz schema | ✅ Done | 90% | baselineRoutes.js | Results feed mastery
BaselineResult.js | Baseline quiz result | 🔶 Partial | 75% | baselineRoutes.js | Wired to mastery update; consumer testing in progress
PracticePaper.js | Practice paper | ✅ Done | 100% | practicePaperRoutes.js | Full CRUD
PracticeQuestion.js | Practice question | 🔶 Partial | 55% | practiceRoutes.js | No Bloom level; not AI-auto-generated
PracticeSection.js | Practice paper section | ✅ Done | 100% | practiceSectionRoutes.js | Full CRUD
PracticeAttempt.js | Practice attempt | 🔶 Partial | 75% | practiceRoutes.js | Feeds mastery via shared assessment writer
TryoutResult.js | AI tryout result | ✅ Done | 90% | aiLearningRoute.js | Feeds mastery
FlashcardResult.js | Flashcard rating result | 🔶 Partial | 45% | — | Ratings persist via applyAssessment; dedicated result rows not used from UI
ExternalResource.js | External study links | ✅ Done | 100% | externalResourceRoutes.js | Full CRUD
SpacedRepetitionSchedule.js | SM-2 review schedule | 🔶 Partial | 65% | spacedRepetitionRoutes.js | SM-2 + cron nudges + recommendation tie-in; not auto-triggered from every result
TeacherLearningPath.js | Teacher learning path | 🔶 Partial | 50% | learningPathRoutes.js | Manual paths; weekly AI study-plan generated separately
StudentProgress.js | Student progress snapshot | 🔶 Partial | 65% | progressRoute.js | Feeds analytics + forecast; reconciliation sweep every 15 min
StudentMemorySummary.js | AI student memory summary | 🔶 Partial | 50% | — | Rolling session-summarise; retention policy incomplete
TutorConversation.js | AI tutor chat session | 🔶 Partial | 55% | aiTutorRoutes.js | Persisted + teacher corrections joined on read; cross-session recall via summary only
ReadingMaterial.js | Reading passage upload | ✅ Done | 100% | readingAssessmentRoutes.js | Full CRUD
ReadingAssessment.js | Reading attempt + scores | ✅ Done | 95% | readingAssessmentRoutes.js | End-to-end pipeline working
WritingPrompt.js | Writing prompt upload | ✅ Done | 100% | writingAssessmentRoutes.js | Full CRUD
WritingAssessment.js | Writing submission + scores | ✅ Done | 95% | writingAssessmentRoutes.js | End-to-end pipeline working
StudentLanguageProfile.js | Adaptive language profile | ✅ Done | 85% | — | Qdrant memory active
── STUDENT WELFARE ─────────────────────────────────────────────────────
StudentBadge.js | Achievement badge | 🔶 Partial | 60% | achievementRoutes.js | masteryEngine award logic; full auto-award UI pending
StudentJournalEntry.js | Personal journal | 🔶 Partial | 40% | — | Model only; no UI
StudentObservation.js | Teacher observation note | 🔶 Partial | 55% | studentObservationRoutes.js | Not linked to intervention
Wellbeing.js | Wellbeing check-in | 🔶 Partial | 40% | wellbeingRoute.js | No safeguard/escalation layer
InterventionLog.js | Teacher intervention record | ✅ Done | 80% | — | Auto follow-up checkpoints + plan templates + automatic improvement + auto-finalize
Behaviour.js | Behaviour incident | ✅ Done | 100% | behaviourRoute.js | Full CRUD
ExcuseLetter.js | Excuse letter submission | ✅ Done | 100% | excuseLetterRoutes.js | Full CRUD
── COMMUNICATION & FINANCE ─────────────────────────────────────────────
ChatThread.js | Real-time chat thread | ✅ Done | 100% | chatRoutes.js | Socket.IO active
ChatMessage.js | Chat message | ✅ Done | 100% | chatRoutes.js | Active
Notification.js | Push notification | ✅ Done | 100% | notificationRoutes.js | Web push + in-app
PushSubscription.js | Browser push sub | ✅ Done | 100% | notificationRoutes.js | VAPID keys active
AlcovePost.js | Academic Alcove post | ✅ Done | 100% | alcoveRoute.js | Full CRUD
AlcoveComment.js | Alcove comment | ✅ Done | 100% | alcoveRoute.js | Full CRUD
AlcoveSubmission.js | Alcove submission | ✅ Done | 100% | alcoveRoute.js | Full CRUD
FeeStructure.js | Fee structure | ✅ Done | 100% | feeRoutes.js | Full CRUD
FeeInvoice.js | Fee invoice | ✅ Done | 100% | feeRoutes.js | Full CRUD
FeePayment.js | Razorpay payment | ✅ Done | 100% | feeRoutes.js | Razorpay integrated
PaymentAudit.js | Payment audit trail | ✅ Done | 100% | paymentSettingsRoutes.js | Full audit log
AuditLog.js | System audit log | ✅ Done | 100% | auditLogRoutes.js | All key events logged
── AI LAYER (added since 2026-08-11) ───────────────────────────────────
MasteryEvent.js | Immutable mastery-change audit | ✅ Done | 90% | masteryRoutes.js | Append-only; source-typed; drives growth + risk reads
MasteryScore history via masteryEventService.js | Transactional score+event writer | ✅ Done | 85% | — | Requires replica set; live verification pending
StudentInsight.js | At-risk / gap / milestone records | ✅ Done | 85% | teacherAnalyticsRoutes.js | Dedupe-key unique index; feeds alerts + plans
WeeklyStudyPlan.js | Persisted weekly study plan | ✅ Done | 80% | weeklyStudyPlanRoutes.js | Generated from mastery + recs; student completion endpoint
GeneratedQuestion.js | AI-generated question bank | ✅ Done | 80% | aiTutorRoutes.js | Teacher save/list/edit/approve; no difficulty calibration
ErrorRecord.js | Per-answer error classification | ✅ Done | 85% | teacherAnalyticsRoutes.js | Concept/Calculation/Reading/Logic; feeds error-breakdown
RecommendationEvent.js | Recommendation lifecycle + impact | ✅ Done | 80% | recommendationRoutes.js | issued→accepted→completed; mastery delta measured; cron finalize
TutorAnswerCorrection.js | Teacher override of an AI answer | ✅ Done | 80% | aiTutorRoutes.js | Separate collection; audited; joined onto student + teacher reads
LongAnswerQuestion.js | Teacher-assigned written question | ✅ Done | 80% | longAnswerAssessmentRoutes.js | Draft→published→closed; class/section/subject targeting; scope-checked
LongAnswerSubmission.js | Student written answer + AI grade + review | ✅ Done | 80% | longAnswerAssessmentRoutes.js | AI evaluator score vs model answer/rubric; needs-review gating; teacher override supersedes
StudentMisconception.js | Per-student misconception model | ✅ Done | 80% | teacherAnalyticsRoutes.js | Recurring same-type errors per topic; auto-resolve on mastery
AdaptivePracticeState.js | Adaptive practice difficulty rung | ✅ Done | 80% | practiceRoutes.js | Resumes per (student,topic); capped 1 rung above mastery band
OutcomeStudy.js | Pre/post outcome measurement | ✅ Done | 75% | teacherAnalyticsRoutes.js | Baseline+post windows, paired effect size; needs real-cohort data to validate

## AI Service Modules
EEC ML — AI Service Modules
Module | Responsibility | What It Does | Status | Progress % | Notes / Gaps
── BUILT ──────────────────────────────────────────────────────────────
documents | Document ingestion | OCR → parse → chunk → embed → Qdrant upsert | ✅ Done | 92% | OCR/parse/chunk/embed/upsert + Bloom/outcome/topic tagging on ingest
parser | Text extract + cleaner | PyMuPDF/Tesseract/docx/pptx; strip teacher notes | ✅ Done | 90% | _strip_teacher_notes + injection stripping active
embeddings | Embedding generation | nomic-embed-text → Qdrant | ✅ Done | 95% | Fully wired
retrieval | Semantic retrieval | Qdrant metadata filters: school/class/section/subject/chapter | ✅ Done | 90% | Metadata filters + hybrid BM25+semantic RRF + Bloom-level filter
chat | RAG tutor — all modes | explain/quiz/flashcards/notes/mindmap/summarize/homework_help | ✅ Done | 90% | All modes; file-based prompt library overrides inline MODE_INSTRUCTIONS
quiz | Quiz generation | 5 MCQ per request via RAG | ✅ Done | 82% | Bloom-target passed from mastery; not saved to question bank
flashcards | Flashcard generation | Q:/A: format via RAG | ✅ Done | 85% | Ratings persist to mastery
summaries | Summary generation | Chapter summaries; OCR + summarize endpoint | ✅ Done | 90% | Working well
assessment | Language eval (Qwen3 8B) | Reading + writing rubric + score JSON | ✅ Done | 90% | Reading + writing rubric scoring
speech | Audio transcription | faster-whisper + SpeechBrain pronunciation | ✅ Done | 85% | faster-whisper + wav2vec2 pronunciation
language_memory | Adaptive language memory | Qdrant student_language_memory; store/retrieve | ✅ Done | 82% | Qdrant student_language_memory store/retrieve
admin | Admin module | Admin-facing AI controls | ✅ Done | 80% | 4 report types (overview / dropout / teacher / integrity) with prompt builders synthesising mastery matrix, teacher effectiveness, dropout risk, cohort trend, content usage, exam integrity -> executive summaries.
── ENGINES — Node-side by design (CLAUDE.md); listed for completeness ──
orchestrator | Central AI coordinator | Node → Orchestrator → engines | ✅ Done | 85% | POST /orchestrate dispatch — generate / generate_questions / evaluate / summarize_session / class_performance
knowledge_graph | Graph traversal | Kahn topo-sort, cycle detection, gap + root-cause traversal, bridge-path | ✅ Done | 85% | ai-service/app/modules/knowledge_graph/ — Kahn topo-sort + cycle detection + gap/root-cause traversal + prerequisite bridge-path. POST /knowledge-graph/analyze + orchestrator task_type graph_analyze + Node client. Tests: test_knowledge_graph.py, knowledgeGraphClient.test.js
bloom | Bloom classifier | Tag documents, questions, answers | ✅ Done | 85% | classifier/bloom.py — tags docs on ingest; question + retrieval integration
mastery_engine | Mastery calculator | accuracy + attempts + time + recency; auto-update | ✅ Done | 100% | N/A as an ai-service module — mastery calc is Node-side by design (masteryEngine.js + masteryEventService.js). Engine complete (feature #18).
error_classifier | Error type classifier | Concept/Calculation/Reading/Logic | ✅ Done | 80% | ai-service classifier + backend/services/errorClassifier.js
gap_detector | Gap detection | Prerequisite traversal → root-cause weak topic | ✅ Done | 100% | In-process engine is Node-side (gapDetectionEngine.js); shared Python traversal now available via knowledge_graph module. Engine complete (feature #24).
recommendation | Recommendation engine | Next topic based on mastery + curriculum graph | ✅ Done | 100% | N/A as an ai-service module — Node-side by design (recommendationEngine.js + recommendationImpactService.js). Engine complete (feature #25).
analytics | AI analytics insights | Per-topic heatmap; at-risk; AI narrative | ✅ Done | 100% | N/A as an ai-service module — analytics is Node-side (classLearningAnalytics.js); AI narrative layer = the admin module above. Features #44, #49.
prompt_library | Prompt directory | externalise all prompts from Python modules | ✅ Done | 85% | ai-service/prompts/ + loader.py (~50 files)
── ADDED SINCE 2026-08-11 ─────────────────────────────────────────────
evaluator | MCQ / written answer scoring | POST /evaluate/answer — marks, rubric, missing concepts, confidence | ✅ Done | 80% | Wired to stored exam + rubric-assignment answers
classifier | Bloom / outcomes / topic | bloom.py + outcomes.py + topic.py — imported by documents + chat | ✅ Done | 82% | Runs on ingest; legacy chunks need re-index
stem | Math answer verification | service.py + verifier.py — arithmetic / unit checks | ✅ Done | 80% | STEM metadata extraction + STEM-aware embedding + rerank_stem_hits wired into hybrid retrieval + AST/sympy answer verifier. Tests: test_stem_service, test_stem_verifier. (Step-by-step solver UI = feature #69, frontend.)
vision | Image understanding | POST /vision/explain-image + PDF-page vision on ingest (client.py) | ✅ Done | 80% | POST /vision/explain-image + PDF-page vision on ingest + student photo flow (POST /api/ai-tutor/explain-photo, SSRF-guarded). Tests: test_vision_client, test_pdf_vision_pages, explainPhoto.test.js

## Summary
EEC ML — Master Progress Summary (2026-09-10)
Domain | Total Features | ✅ Done | 🔶 Partial | ❌ Not Started | Next Action
Core AI Pipeline | 6 | 6 | 0 | 0 | Done — orchestrator, hybrid search, prompt library all live
Content Intelligence | 5 | 5 | 0 | 0 | Re-index legacy chunks for Bloom/outcomes; finish doc-versioning UI
Assessment & Evaluation | 6 | 6 | 0 | 0 | Live replica-set DB verification of the mastery/evaluator pipeline
Mastery & Memory | 6 | 6 | 0 | 0 | Validate forecasts on longitudinal data; academic-memory retention policy
Gap & Learning Path | 4 | 4 | 0 | 0 | Wire recommendation widget to accept/complete; AI bridge-path generation
AI Content Generation (Student) | 9 | 9 | 0 | 0 | Personalise worksheets to mastery gaps; adaptive item selection
AI Content Generation (Teacher) | 4 | 4 | 0 | 0 | Teacher UI for Bloom/difficulty selection; surface override affordance
Language Assessment | 3 | 3 | 0 | 0 | Real-device mic testing; surface language profile card
Analytics & Intelligence | 7 | 7 | 0 | 0 | Teacher dashboard cards for engagement + at-risk; narrative-quality eval
Research-Grade Features | 14 | 9 | 5 | 0 | Practice/homework confidence check-ins; teacher UIs for belonging + learning-style; equity-monitoring admin UI; path-selection UI for Student Agency
Future Features | 9 | 7 | 2 | 0 | Frame/vision analysis for Video Understanding; interactive quiz UI reuse for video quiz; dedicated math model (deferred pending decision)
TOTAL | 73 | 66 | 7 | 0
Overall: 66 Done + 7 Partial + 0 Not Started out of 73 (90% fully done, 100% at least started)
Re-audited 2026-09-10 against the AI-layer build (see AI_UNTOUCHED_FEATURES_CHECKLIST.md)
Core learning-intelligence engines (orchestrator, hybrid search, Bloom, error classifier, gap detection, mastery auto-update, recommendations, study plan) now built; remaining gaps concentrate in safety/governance, quality monitoring, and training-data infra
TOP 5 PRIORITIES (2026-09-10)
1. Safety & governance UI polish | Escalation engine + consent gating are already built (EscalationCase/escalationService.js, aiConsentService.js) — remaining work is dashboard UI for leadership/counsellors, not the underlying safety logic
2. AI quality & cost monitoring | Latency / token / cost / version logging; grounding + hallucination measurement
3. Training-data pipeline | Interaction-logging schema, redaction, dataset versioning, model registry + rollback
4. Frontend wiring | Recommendation accept/complete widget, teacher AI-override UI, unified health card
5. Model + prompt version logging | Log which model / prompt / retrieval config produced each AI output (feeds quality + training-data work)

## Implementation Steps
Step | Feature | Current progress | Remaining gap | Acceptance check
1 | ML Engine (weighted EMA mastery, at-risk detection, class trends) | 80% | Event-stream EMA and attendance-aware risk bands are live; forecast accuracy still needs longitudinal validation. | Run against longitudinal fixture data and record accuracy/error metrics.
2 | AI-generated Learning Path (bridge from gap → target topic) | 55% | Weekly plan generated from mastery + recs; AI bridge-path for an arbitrary gap→target still limited | Implement the gap, add a focused regression test, and verify the related API/UI flow.
3 | Worksheet / Homework Generation (personalised to mastery gaps) | 50% | POST /api/ai-teacher/worksheet generates worksheets; not personalised to individual mastery gaps | Implement the gap, add a focused regression test, and verify the related API/UI flow.
4 | Adaptive Difficulty (adjust question hardness based on mastery) | 60% | Mastery-derived Bloom band drives question difficulty; no full IRT/adaptive item selection | Implement the gap, add a focused regression test, and verify the related API/UI flow.
5 | AI Question Paper Generator (teacher selects topic + Bloom) | 55% | Bloom-level question generation exists (bloom_question.txt); teacher UI for Bloom/difficulty selection pending | Expose the workflow in the relevant portal UI and add a user-flow test.
6 | Retention / Forgetting Model (knowledge decay over time) | 65% | SM-2 schedules now expose an exponential retention estimate and fading/at-risk status through /api/spaced-repetition/retention; chart UI remains. | Expose the workflow in the relevant portal UI and add a user-flow test.
7 | Misconceptions Engine (explicit error model per topic/student) | 45% | Class-wide misconception aggregation (classMisconceptions) + misconception tutor mode; per-student explicit misconception model pending | Implement the gap, add a focused regression test, and verify the related API/UI flow.
8 | Multidimensional Engagement (situational + behavioural + emotional) | 65% | Behavioural, recency-based situational, and optional wellbeing-based emotional dimensions are available; dashboard presentation remains. | Expose the workflow in the relevant portal UI and add a user-flow test.
9 | Student Agency (learner control over learning path) | 20% | Student can accept/dismiss/complete recommendations; no learning-path selection UI | Expose the workflow in the relevant portal UI and add a user-flow test.
10 | Explainable AI (why did AI recommend / answer this?) | 25% | Recommendations carry an explainability string; no reasoning-trace/lineage logging for tutor + evaluator | Implement the gap, add a focused regression test, and verify the related API/UI flow.
11 | Evidence Testing (prove platform improves learning outcomes) | 25% | Assessment-evidence summaries + daily regression forecast infra; no pre/post outcome-measurement framework, forecast unvalidated | Run against longitudinal fixture data and record accuracy/error metrics.
12 | AI / Data Ethics Framework (child-centered, beyond RBAC) | 20% | JWT + RBAC + tenant isolation; no child-ethics/consent framework | Add the policy model/enforcement, audit event, and negative authorization tests.
13 | Image Understanding (student uploads photo of problem) | 50% | vision module: POST /vision/explain-image + PDF-page vision on ingest + visual_explain mode; student photo-of-problem upload flow pending | Implement the gap, add a focused regression test, and verify the related API/UI flow.
14 | Math Solver (step-by-step equation solving) | 40% | stem module + stem/verifier.py math-answer verification; step-by-step solving UI + dedicated math model pending | Expose the workflow in the relevant portal UI and add a user-flow test.
15 | Topic Failure Prediction (predict fail before test happens) | 25% | learningEvidenceService.forecastScores infra; not validated, not surfaced | Expose the workflow in the relevant portal UI and add a user-flow test.
16 | Performance Forecasting (predicted score on next test) | 30% | Daily least-squares score forecast (forecast-v1) + class forecast; accuracy not validated on longitudinal data | Run against longitudinal fixture data and record accuracy/error metrics.
17 | At-risk / Dropout Risk Prediction (ML model) | 50% | Attendance + mastery + trend risk factors and an interpretable dropout-risk band are live; a dedicated trained model still needs longitudinal validation. | Run against longitudinal fixture data and record accuracy/error metrics.